## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/7 - 9/20 | Github setup, Project idea finalized, Roles assigned, and SPPP DOC finalized | No serious tech issues reported | team 4 team name and logo still in process of being developed | still in development phase
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Christol
Your Lead Roles: Primary: design leader, Backup: configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time

## Ignacio Moral
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirements Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | Time for type 0 tasks | Time for type 1 tasks | Time for type 2 tasks | Time for type 3 tasks | Time for type 4 tasks | Time for type 5 tasks | Time for type 6 tasks | Time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/04/2022-09/10/2022
2 | 09/11/2022-09/17/2022 | 5 | 3 | 2

## Tsing
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 8 | 6 | 2 | 0 - learn java, express 1 - define high level requirements, 3 - talk about git flow, development flow, tools 6 - set up git 7 - research similar products, prepare presentation | 2 | 1 |  | 2 |  |  | 0.5 | 0.5 | 1. come up with git flow, development flow, some tools 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation 4、rearch vercel,figma,security tools | 1. not familar with communicate(no experience before) 2、not familar with new tools | 1. try to talk my opinions or views 2、spend more time to study | 1、determine some criteria about development 2、go for studying new tools or languages | 6
1 | 9/7 - 9/13 | 0 | 0 | 0
2 | 9/14 - 9/20 | 0 | 0
3 | 9/21 - 9/27 | 0 | 0
4 | 9/28 - 10/4 | 0 | 0
5 | 10/5 - 10/11 | 0 | 0
6 | 10/12 - 10/18 | 0 | 0
7 | 10/19 - 10/25 | 0 | 0
8 | 10/26 - 11/1 | 0 | 0
9 | 11/2 - 11/8 | 0 | 0
10 | 11/9 - 11/15 | 0 | 0
11 | 11/16 - 11/22 | 0 | 0
12 | 11/23 - 11/29 | 0 | 0
13 | 11/30 - 12/6 | 0 | 0
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM

## Ryan Burns
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: Primary Team Leader, Back up: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
example | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/7 - 9/13 | 3 | 2 | 1 | 0-Spent time refamiliarizing myself with GitHub, git commands, and created our repository | 2 | [7 empty] | 1. Ran kickoff meeting and took minutes 2. Set up git, commit a test message on git | 1. Ran into a problem merging lab1 into main branch. Christol found a solution | 1. test GitHub on my own to become more comfortable with roadblcoks | 0 - Have first in person meeting 1 - choose a role - either requirement leader, QA leader... 2 - have SPPP document complete by Sunday 3 - refamiliarize myself with JavaScript & VSCODE | 7
2 | 9/14 - 9/20 | 5 | 3 | 2 | 0 - Reviewed documentation and Reviewed Team Leader Role 1 - SPP Research 2 - learning | 1 | 0.5 | 1.5 | [5 empty] | 0 - Created agenda for Sunday's meeting to "divide and conquor the SPPP document 1 - Researched already existing sites that already provide similar services to our project 2 - learning React | 0 - Creating an agenda that covered all aspects of SPPP doc was challenging 1- I could only go so far into an application without signing up for the service to fully understand what it offers 2- A bit of a learning curve for react | 2- keep on practicing with react | 0- Make sure all leaders are on the same page on their tasks 1- Start build of welcome page with necessary features. 2- Have team starting to think about what design pattern to use for our project 3- Learn more about QA leader role so I can be back up. 4- Learn more about React and Heroku | 4
3 | 9/21 - 9/27 | 0 | 0
4 | 9/28 - 10/4 | 0 | 0
5 | 10/5 - 10/11 | 0 | 0
6 | 10/12 - 10/18 | 0 | 0
7 | 10/19 - 10/25 | 0 | 0
8 | 10/26 - 11/1 | 0 | 0
9 | 11/2 - 11/8 | 0 | 0
10 | 11/9 - 11/15 | 0 | 0
11 | 11/16 - 11/22 | 0 | 0
12 | 11/23 - 11/29 | 0 | 0
13 | 11/30 - 12/6 | 0 | 0
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM

## Zahit
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: QA Leader, Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/7 - 9/13 | 5 | 3 | 2 | 0 - reading some git and github documents 1 - looking for some project ideas | 1 | 2 | [6 empty] | 1- Set up git and commit to project repo 2- Timekeeper at meeting 2 |  |  | 0 - Decide a project 1 - Choose a project role 2 - Research the topics related with project role | 10
2 | 9/14 - 9/20 | 10.5 | 9.5 | 1 | 0 - Research about project functions and requirements 1 - Research about branching strategies 2 - Research about QA Plan and tools 3 - Write QA Plan in SPPP 4 - Prepare a part of presentation in SPPP | 2 | 1 | 4 | 1 | 1.5 |  |  |  | 1 - Acquired QA Leader role and backup Project Leader Role 2 - Timekeeper and minutestaker at meeting 3 3 - Write Timeline in Management Plan and QA Plan sections in SPPP | 1 - Essential Features may be extended during Iteration 1 |  | 1- Set up Prettier and ESLint 2- Contribute setting up feature branches 3- Integrate Prettier + ESLint and Unit Tests in pre-commit hook 4- Main Page Design | 15
3 | 9/21 - 9/27 | 0 | 0
4 | 9/28 - 10/4 | 0 | 0
5 | 10/5 - 10/11 | 0 | 0
6 | 10/12 - 10/18 | 0 | 0
7 | 10/19 - 10/25 | 0 | 0
8 | 10/26 - 11/1 | 0 | 0
9 | 11/2 - 11/8 | 0 | 0
10 | 11/9 - 11/15 | 0 | 0
11 | 11/16 - 11/22 | 0 | 0
12 | 11/23 - 11/29 | 0 | 0
13 | 11/30 - 12/6 | 0 | 0
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM

## Nivan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly. | [13 empty] | Don't spend more than 10 min on this
Your Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 9/7 - 9/13 | 4.5 | 3 | 0 |  | 2 | 1 |  |  |  |  | 0.5 | 1 |  |  |  |  | 7
2 | 9/14 - 9/20 | 3.5 | 3.5 |  |  | 1 | 1 |  |  |  | 0.5 |  | 1
3 | 9/21 - 9/27 | 0 | 0
4 | 9/28 - 10/4 | 0 | 0
5 | 10/5 - 10/11 | 0 | 0
6 | 10/12 - 10/18 | 0 | 0
7 | 10/19 - 10/25 | 0 | 0
8 | 10/26 - 11/1 | 0 | 0
9 | 11/2 - 11/8 | 0 | 0
10 | 11/9 - 11/15 | 0 | 0
11 | 11/16 - 11/22 | 0 | 0
12 | 11/23 - 11/29 | 0 | 0
13 | 11/30 - 12/6 | 0 | 0
14 | 12/7 - 12/13 | FINAL PRESENTATION
15 | 12/14 - 12/20 | STUDY PERIOD (NO CLASS)
16 | 2022-12-21 | FINAL EXAM